## Sheet1
URL | https://ensekautomationcandidatetest.azurewebsites.net
Description | ENSEK test website.
Test Number | Scenario | Expected Result | Actual Result | Pass/Fail | Bug Reference
1 | All links work | All links work as expected | The contact link and the Sell Energy links both load to unfinished pages | Failed | 1, 2
2 | Mobile navigation bar links all function | All links work as expected | The contact link and the Sell Energy links both load to unfinished pages | Failed | 1, 2
3 | Home page alignment | The home page elements are aligned | The button below the About Us is higher than it should be | Failed | 3
4 | Spelling and grammar | Spelling and grammar is good and consistent | Homepage talks about surpless energy rather than surplus energy | Failed | 4
5 | Errant text | All text is appropriate for each page | [For Candidate Testing Purposes Only] appears on every page | Resolved | This isn't an issue because this text makes sure that everyone who visits it knows that it is for testing candidates only.
6 | Register for an account | Can register a new account | After 44 seconds there is a 500 error | Failed | 5
7 | Bad Login | A bad login will produce a readable error message | After 30 seconds there is a 500 error | Failed | 6
8 | Errors displayed externally | Errors are customer fields | We are displaying the complete error report externally which is a security risk | Failed | 7
9 | The time is | This should be local time | Is GMT | Query | See Test Plan Issues Noted, But Not Raised
10 | Percentile discount | The discount should be consistent | It is unclear if this is two separate discounts or the same. | Failed | 8
11 | Buy Energy page alignment | Alignment is always good | Alignment has problems on mobile portrait view | Failed | 14
12 | Login page relevant components | The login page shouldn’t have any unnecessary components | There is a link to an ASP.NET article | Failed | 15
13 | Login page validation | Username and password fields should have validation | The username field has validation | Passed
14 | Buy Energy title has full stop | There hsould be a full stop in the title to be consistent with other pages | No full stop | Failed | See Test Plan Issues Noted, But Not Raised
15 | Register page email field has validation | This field has useful validation | As expected | Passed
16 | Register page password fields have validation | These fields have useful validation | As expected | Passed
17 | Buy Energy invalid input | The page should display a customer friendly error message | There is an error page | Failed | 9
18 | Buy Energy negative input | Negative input should not be allowed | It is possible to give back energy | Failed | 10
19 | Buy Energy large input | The range of input shoul dbe capped | It is possible to purchase more energy than is available | Failed | 11
20 | Buy Energy Spelling | Spelling and grammar are good | Quantity is incorrectly spelt | Failed | 12
21 | Login Page Mobile Compatibility | Web page looks good and is responsive on mobile | There are layout issues | Failed | 13
22 | Buy Energy Mobile Compatibility | Web page looks good and is responsive on mobile | There are layout issues | Failed | 14